## ProductBacklog
PRODUCT BACKLOG TEMPLATE
PRODUCT BACKLOG REPORT
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
1 | non register customer | view the car list | know which car is available | High | 1 | Not Started | Not Started | High
2 | non register customer | know the price | know how much I need to pay for rent | High | 1 | Not Started | In Progress | Medium
3 | non register customer | register account | have a account to rent a car | High | 1 | Not Started | Complete | Low
4 | register customer | login account | manage my own account | High | 1 | Not Started | Overdue
5 | register customer | search popular items and car photos | better choose the car | Medium | 1 | Not Started | On Hold
6 | register customer | filter number of people that can sit in the car | specify preferences | Medium | 1 | Not Started
7 | register customer | be able to filter cars by colour | specify my preferences | Medium | 1 | Not Started
8 | register customer | add/remove multiple car items | specify what I want to rent | Medium | 1 | Not Started
9 | register customer | see the details of my booking | know the status of the booking | Low | 2 | Not Started
10 | register customer | make the payment | secure the booking | High | 1 | Not Started
11 | register customer | Be reminder of upcoming booking | aware of the booking | Low | 2 | Not Started
12 | register customer | be able to rating | share my experiences | Low | 2 | Not Started
13 | register customer | write opnions | write what I liked/did not like | Low | 2 | Not Started
| register customer | update profile | profile become more complete | Low | 2 | Not Started
14 | Admin | manage the agencies | know agencies details | High | 1 | Not Started
15 | Admin | view the feedback | improve the system | Low | 2 | Not Started
16 | Agencies | manage the car list | update/remove cars details | High | 1 | Not Started
17 | Agencies | add promotions | customer know the promotions | Medium | 2 | Not Started
18 | Agencies | manage customers bookings | customer get the booking status | Medium | 2 | Not Started
19 | Agencies | chat with customer | derect update them the enquries | Low | 2 | Not Started
20 | Agencies | be reminder of upcoming booking | aware of the booking | Low | 2 | Not Started
21 | Agencies | get the rental report | know sales or revenue | High | 1 | Not Started
22 | Agencies | reject customer booking when tha car is not available | let customer choose another car | Medium | 2 | Not Started
23 | Agencies | view the feedback | improve the system | Low | 2 | Not Started
TOTAL |  |  |  |  | 36

## SprintBacklog 1
AGILE SPRINT BACKLOG TEMPLATE
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Design interface | 5 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #2
Design interface | 5 | Lim Chien Hui | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3
Design interface | 4 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 5 | Thean Ru Xin | Not started | 2 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 2 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #4
Design interface | 4 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 5 | Lim Chien Hui | Not started | 2 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Lim Chien Hui | Not started | 2 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #5
Design interface | 5 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #6
Design interface | 5 | Lim Chien Hui | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #7
Design interface | 5 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #8
Design interface | 4 | Lim Chien Hui | Not started | 2 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #10
Design interface | 5 | Lim Chien Hui | Not started | 2 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #14
Design interface | 5 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #16
Design interface | 5 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #21
Design interface | 4 | Thean Ru Xin | Not started | 2 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 129 | 0 | 0 | 0 | 0 | 0

## SprintBacklog 2
AGILE SPRINT BACKLOG TEMPLATE
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #9
Design interface | 5 | Lim Chien Hui | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Thean Ru Xin | Not started | 5 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #11
Design interface | 4 | Lim Chien Hui | Not started | 2 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Thean Ru Xin | Not started | 5 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #12
Design interface | 4 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #13
Design interface | 4 | Lim Chien Hui | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #15
Design interface | 4 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #17
Design interface | 5 | Lim Chien Hui | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #18
Design interface | 5 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #19
Design interface | 5 | Lim Chien Hui | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #20
Design interface | 4 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #22
Design interface | 5 | Thean Ru Xin | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 2 | Lim Chien Hui | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #23
Design interface | 4 | Lim Chien Hui | Not started | 3 | 0 | 0 | 0 | 0 | 0 | 0
write back-end code | 8 | Thean Ru Xin | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
link to database | 5 | Lim Chien Hui | Not started | 4 | 0 | 0 | 0 | 0 | 0 | 0
Testing | 1 | Thean Ru Xin | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 125